## bugs-2025-01-01
bug_id | bug_severity | priority | op_sys | assigned_to | bug_status | resolution | short_desc
4 | minor | Low | Windows | deepa@gmail.com | ASSIGNED | --- | check the close button by clicking any other place
26 | minor | Low | Windows | deepa@gmail.com | ASSIGNED | --- | check login button with any special charecters except (@$_) in password
18 | minor | Low | Windows | harshida@gmail.com | ASSIGNED | --- | check login button with only alphabets in username
23 | minor | Low | Windows | harshida@gmail.com | ASSIGNED | --- | check login button with only special characters in password
14 | minor | Low | Windows | pritesh@gmail.com | ASSIGNED | --- | check login button with password is correct but username is incorrect
9 | minor | Low | Windows | vandita@gmail.com | ASSIGNED | --- | check username and password with wrong value
28 | minor | Low | Windows | yash@gmail.com | ASSIGNED | --- | check login button with all capital lattes only password
7 | normal | High | Windows | pritesh@gmail.com | RESOLVED | FIXED | check the reset app button
16 | minor | Low | Windows | deepa@gmail.com | RESOLVED | FIXED | check login button with only digital in username
24 | minor | Low | Windows | deepa@gmail.com | RESOLVED | FIXED | check login button with only alphabets in username
27 | minor | Low | Windows | harshida@gmail.com | RESOLVED | FIXED | check login button with all capital lattes only username
25 | minor | Low | Windows | pritesh@gmail.com | RESOLVED | FIXED | check login button with maximum numbers of charecters in username
8 | minor | Low | Windows | vandita@gmail.com | RESOLVED | FIXED | check username and password with blank
12 | minor | Low | Windows | vandita@gmail.com | RESOLVED | FIXED | check login button with username is correct but password is incorrect
6 | critical | Highest | Windows | vandita@gmail.com | VERIFIED | FIXED | check login button by using different possibilities
3 | critical | High | Windows | harshida@gmail.com | VERIFIED | FIXED | check finish button its show payment message without order
17 | minor | Low | Windows | deepa@gmail.com | VERIFIED | FIXED | check login button with only special characters in username
15 | minor | Low | Windows | pritesh@gmail.com | VERIFIED | FIXED | check login button with white spaec between in only username
11 | minor | Low | Windows | vandita@gmail.com | VERIFIED | FIXED | check login button with password is correct but blank username
13 | minor | Low | Windows | vandita@gmail.com | VERIFIED | FIXED | check login button with username is correct but password is incorrect
1 | minor | Low | Windows | yash@gmail.com | VERIFIED | FIXED | check add to cart menu by click on that change the position
21 | minor | Low | Windows | yash@gmail.com | VERIFIED | FIXED | check login button with white spaec between in only password
22 | minor | Low | Windows | yash@gmail.com | VERIFIED | FIXED | check login button with only digita in password
2 | critical | High | Windows | nirali@gmail.com | CLOSED | FIXED | check all item menu not show any change
5 | minor | Low | Windows | harshida@gmail.com | CLOSED | FIXED | check the filter button
19 | minor | Low | Windows | harshida@gmail.com | CLOSED | FIXED | check login button with maximum numbers of charecters in username
20 | minor | Low | Windows | harshida@gmail.com | CLOSED | FIXED | check login button with any special charecters except (@$_) in username
10 | minor | Low | Windows | vandita@gmail.com | CLOSED | FIXED | check login button with username is correct but blank password